## Sheet1
Risk | Occurrence | Responasible Parties | Grade Impact | Time Impact | Plan of Action
Not turning up to meetings | Mid | Adam/Gabryel | Low | Low | If after 3 not agrared concuative group misses contact Shirely and cc them in
Conflit between group menmbers | Low | Everyone | High | High | We will hold a team meeting to resolve these issues
Weather risk | Mid | Reece | Mid | Mid | We will post on the discusion board if we are unable to attend due to these reasons
Equiment not working | High | Everyone | High | High | We will contact Shirely
Network issues | Mid | Everyone/ Adam | Mid | Mid | Comuncate when issues arise so group can work around
Oversight of task difficulty | High | Everyone | Low | High | Reavaulte tasks on discovery
Family issues | Mid | Everyone | High | High | Inform group when issues arise, group will take into consideration when asigning work
Miss understanding tasks | Mid | Everyone | High | High | To reduce risk we will say back what task was that was assign to us and if this does happen 'Tell them and clarify the task'
Gold plating | Mid | Everyone | Low | High | Make sure we consult the backlog before we add cool features
Changes to requirments | Mid | Everyone | Low | High | Discuss as group